## Asp.net Estimation
|  | ESTIMATE SHEET | Total Recall
|  | Total Hours * | 70
|  | Working days | 12 | Days
Sr No | Task | Sub-Task | Hours | Remarks | Query | Answers
1 | Get Fields from Configuration
|  | Create Field Types | 2
|  | Create Field general configuration | 3
|  | Read Configuration | 2 | All configuration will be read and according to the propeties | How I will read configuration? is it from database?
|  | Generate Form on Web | 6 | A web form will be designed according to Configuration
2 | General Help Configuration
|  | Document Number | 2
|  | General help Window | 6 | A new window will open and according to document number result will be searched and data will be listed according the search
|  | Chnages value by pressing F4 | 2
|  | Bind Result in Fields | 3
3 | User Inter face
|  | New Document | 5 | New Document,Form generation and save data
|  | Advance Search | 8 | Select another filter,Comparision,value
|  | Show result in The Grid | 3 | Searched data will be binded in grid view
|  | New pop up navigate | 2 | A window will be generated where user can search the data
|  | Generate Form | 2 | After search form will display the result
|  | Bind Data | 3
|  | Pagination | 4 | next, previous or manual Entry is allowed
|  | search and Delete Document | 3 | Data will be searched and selected data will be deletd
|  | Header Section | 3 | Data will shown on Form | when to find Field.SectionType = 'E' or Field.SectionType = 'd'?
|  | Details Section | 3 | Data will shown on Grid view
4 | Field Help Configuration
|  | Text Filed type Additinal Configuration | 4 | Additional configuration proprtie will be configured
|  | Number Type Additional Configuration | 4
| NOTE: | Terms and Conditions |  | Estimate is tentative and actual hours can be 15 % plus(+) or minus(-) of given estimate in hours